TRANSFER PROQUALINDT

TRANSFERRING EUROPEAN TRAINING PROGRAMME FOR THE QUALIFICATION OF NON-DESTRUCTIVE TESTINGS PERSONNEL

ANNEX B

| WORK PACKAGES AND MAIN LANDMARKS | 2011 |  |  | 2012 |  |  |  |  |  |  |  |  |  |  |  | 2013 |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 |  |  |  |
|  | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D |
| MANAGEMENT, COORDINATION AND EVALUATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1st meeting in Cartagena (Spain) (8 and 9 February 2012) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Products: Working Methodology, Quality Plan and Style Manual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Intermmediate (30th Nov 2012) and final report (30th Nov 2013) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| REVIEW AND UPDATE |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2nd meeting in Lisbon (Portugal) (12 and 13 September 2012) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Products: Didactic Guides (English nad Spanish) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Products: Study Manuals, Teacher's Guide (English and Spanish) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| TRANSFER AND TRANSLATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Products: Didactic Guides (Hungarian, Croatian, Czech and Portuguesse) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Products: Study Manuals, Teacher's Guide (Hung, Croat, Czech and Port.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| EDITION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3rd meeting in Praga (Czech Rep.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Products: Didactic Guides, Study Manuals, Teacher's Guide |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| DISSEMINATION AND PUBLICITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4th meeting in Zagreb (Croatia) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Products: Leaflets and web page |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Table 1

Picture 1 and table 1 describe respectively the structure and the development of the project. The project is divided in the following work packages:

WORK PACKAGE 1: 	MANAGEMENT, COORDINATION AND EVALUATION.

This work package aims at the existence of a continuous contact between partners, ensuring that all aspects of economic and administrative management of the project are controlled, to take the necessary decisions on technical levels and / or political, so as to ensure the pace and development of the project and to ensure the prompt correction of the deviations that could arise with respect to the formulation or any possible dispute among the partners.

Furthermore, the evaluation, which is very prominent and important for partners, aims to be performed continuously, so as to achieve the project objectives without difficulty, playing all members an active role in this area. To this end, a quality plan will be designed that allows us to measure the degree of compliance with the objectives and conduct a continuous evaluation of the achievements. The work package consists of the direction, coordination and continuous monitoring of the project throughout the implementation period, and within it will take place:

- The development and adoption of a document that contains the working methodology to be followed during the project, which will be agreed by all partners, and it will be used as a basis for development.

- Fixing the way of approving the various documents generated in the course of the project.

- The successful completion of the project will be analyzed and will ensure the involvement of all partners and potential beneficiaries.

- The quality of products resulting from the project will be ensured.

- It will be established the type and number of assessments to ensure compliance with the targets, implementing a quality

- Activities descriptions. Tasks.

-Launch of the project: This is a first contact among the partners at the headquarters of the promoter, which will be used to present the project and deepen in it. At this meeting, to be attended by all partners and will mark the beginning of TRANSFER PROQUALINDT, it will be established by consensus all aspects of economic and administrative management of the project, as well as guidelines in their development as the way of behaving of each partner, their responsibilities and how the decisions will be made. All this will be reflected in a document called Work Methodology. Mentioned document will include the Quality Plan already mentioned. It will also be exposed the starting point of the work to be carried out in the different phases of the project and will be defined, broadly speaking, the specific objectives of the project, its scope and the role the partners will play in the different work packages and activities to be undertaken during the project (division of tasks). It must also be approved and defined the guidelines and the various aspects that are included in the style manual.

-Working Group for monitoring and evaluation of the project: Consists of staff members belonging to different technical levels and / or political decision, in order to be able to make decisions that result in the smooth pace and project development and correction of deviations that could arise regarding the formulation. The working group will meet after the meetings / events that will take place within the different work packages, and will be the framework for the adoption of agreements, fixing aspects and evaluate the progress of the project.

In order to unify and standardize the final products to be obtained, it will be used the Style Manual, which was developed in the project PROQUALINDT. The CNFPO will be responsible for review and posting to other partners.

| WP1 |  | P0 (CNFPO) | P1(CNDT) | P2 (AEND) | P3 (CrSNDT) | P4(MAROVISZ) | P5(RELACRE) | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Staff costs | 8640 | 6822 | 8130 | 8040 | 5442 | 7920 | 44994 |
|  | Travel | 0 | 2848 | 1848 | 2848 | 2848 | 2448 | 12840 |
|  | Subcontracting | 9000 |  |  |  |  |  | 9000 |
|  | Equipment |  |  |  |  |  |  | 0 |
|  | Others |  |  |  |  |  |  | 0 |
|  | Indirect costs | 750 | 750 | 750 | 750 | 750 | 750 | 4500 |
|  | Total | 18390 | 10420 | 10728 | 11638 | 9040 | 11118 | 71334 |

WORK PACKAGE 2:	 	REVIEW AND UPDATE

- The aim of the work package is the review and updating of materials resulting from the reference project PROQUALINDT.

- It would indeed be the AEND responsible for leading this work package, mainly due to two reasons: first, because along with the CNFPO is the only member of the Association who participated in the project that is used as reference, so they have a better understanding of the structure and scope of content;

- Therefore, the objective is, on one hand, to ensure that the contents are structured as described in the didactic guides, and, on the other, the full review of study guides, making in them the necessary modifications so that the contents are properly updated and in accordance with European standards governing the training of NDT operators.

- Activities descriptions. Tasks.

The starting point for the revision of existing materials will be the didactic guides. As mentioned above the weight of this phase shall be on the AEND, but throughout its duration will have the support of the other partners. In particular the actions to take are as follows:

- Review of the teaching guides in that the contents are well structured and updating according to standard if necessary, the timings for each of the subjects and the minimum requirements of facilities, students and teachers. The revision of the guides will be carried out in parallel to the Spanish and English version. In this regard, in the 1 st meeting the didactic guides in English will be provide to the other partners, so they too can make suggestions and help in this initial review process.

- Review of study manuals for the five methods developed. Given the complexity of this task, the volume of work involved, the AEND will periodically send to the rest of the partners, the already reviewed and updated methods when finished, to enable partners to start the validation tasks and parallel translation. At this stage the AEND have the double task of reviewing the texts in Spanish and translate the changes made to the texts in English, with which partners will work.

- Revision of the teacher's guide and update if necessary.

In the second half of this work package, the 2nd meeting of all partners will be held, which will take place in Portugal, at the headquarters of RELACRE. The purpose of this meeting is to ascertain the degree of progress of the project, making a more accurate estimate of the total length thereof, and to validate the translation work that has already been made.

| WP2 |  | P0 (CNFPO) | P1(CNDT) | P2 (AEND) | P3 (CrSNDT) | P4(MAROVISZ) | P5(RELACRE) | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Staff costs | 2880 | 2274 | 2710 | 2680 | 1814 | 2640 | 14998 |
|  | Travel | 2416 | 2816 | 1816 | 2816 | 2816 |  | 12680 |
|  | Subcontracting |  |  | 23000 |  |  |  | 23000 |
|  | Equipment |  |  |  |  |  |  | 0 |
|  | Others |  |  |  |  |  |  | 0 |
|  | Indirect costs | 250 | 250 | 250 | 250 | 250 | 250 | 1500 |
|  | Total | 5546 | 5340 | 27776 | 5746 | 4880 | 2890 | 52178 |

WORK PACKAGE 3:	 	TRANSFER AND TRANSLATION

- The main objective of this work package is the transfer of material already reviewed (guides and manuals) to other partners to proceed to translate to their languages.

- Obviously the weight of this phase rests with the respective organizations of the Czech Republic, Hungary, Croatia and Portugal.

- Activities descriptions. Tasks.

- The starting point for this phase is located approximately after three months at the beginning of the project and once the responsible members of this package have already begun to receive some of the materials and revised and translated into English, so at this point it will be possible to have a better idea of how the work will be done. Basically the activities to be carried out are as follows:

- CNDT, MAREVISZ, CrSNDT and RELACRE will translate into their languages (Czech, Hungarian, Croatian and Portuguese respectively), the didactic guides once confirmed, incorporating to each of them, if necessary, those aspects that may be unique to each of the countries, taking care at all times not to distort the original texts and of course in accordance with European standards of reference.

- Also, they will then proceed as they receive the study manuals, and once these have already been validated, their translation into their languages.

- Once the process of translating materials has started, and given the specificity of the terminology used, is likely that some questions could arise, comments and suggestions. It is at this point that the work of the AEND on one hand, to try to resolve these issues, and the CNFPO as coordinator to arbitrate communications that occur will be essential for the proper conduct of this phase.

| WP3 |  | P0 (CNFPO) | P1(CNDT) | P2 (AEND) | P3 (CrSNDT) | P4(MAROVISZ) | P5(RELACRE) | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Staff costs | 2880 | 2274 | 2710 | 2680 | 1814 | 2640 | 14998 |
|  | Travel |  |  |  |  |  |  | 0 |
|  | Subcontracting |  | 8000 |  | 8000 | 8000 | 8000 | 32000 |
|  | Equipment |  |  |  |  |  |  | 0 |
|  | Others |  |  |  |  |  |  | 0 |
|  | Indirect costs | 250 | 250 | 250 | 250 | 250 | 250 | 1500 |
|  | Total | 3130 | 10524 | 2960 | 10930 | 10064 | 10890 | 48498 |

WORK PACKAGE 4:		EDITION

- This work package is twofold. On the one hand and as a step prior to initiation, conduct a final review of the contents of all material already translated. On the other hand there will be a second review, in this case designed to look after the appearance of the texts, so that they comply with what was stated in the manual of style that serves as a reference and mandatory for all. So it will be the duty of each member, to perform this review on the materials they have worked. Finally, this package includes the development with own means of the resulting products, which may be available electronically and on paper.

- Activities descriptions. Tasks.

- Based on the above goals, the activities to be carried out during this phase are as follows:

- To perform a final check of the contents of the resulting materials, not only guides but also study manuals and teacher's guide. To this end, a term will be opened to allow any amendments or corrections previously agreed among the partners. Each partner is responsible for conducting the review of the materials with which they have worked. In the case of the Spanish and English, the CNFPO will work with the AEND to alleviate this task as much as possible. After finishing the above deadline, it will not be possible to make any modification in the contents of the texts. At this point a new review process will begin, which will aim to refine the appearance of the texts (numbering of pages, including tables and images in the text, fonts, margins, ...), and adapt the materials as mandated in the manual of style, to which all members are obliged to give to the resulting product a homogeneity, regardless of the language in which they are written. To this end, and looking for this homogeneity, the CNFPO will design the covers and cover arts of all products, and will be forwarded to each of the partners.

- At the beginning of this phase and before starting the final edition, whether it is on CD or on paper, the 3rd international meeting will be held, at the headquarters of the Czech partner, and at that meeting will be presented the drafts of all materials in different languages. In this meeting the evaluation and validation of all materials will be decided, and all the definitive agreements will be decided with a view to publishing. It will also be outlined the strategy for dissemination of the project by each partner.

- Finally, each partner will have all the materials in electronic files, ready for printing or burning to CD, and they will get at least five copies of the tutorials on paper, and ten copies of CDs containing all the materials dealt (guides, study manuals and teacher's guide). Both the guides on paper and the CD´s will be developed by each of the partners with their own resources. In the Spanish case, for the manufacture of products in Spanish and English, this task is shared jointly by the AEND and CNFPO.

| WP4 |  | P0 (CNFPO) | P1(CNDT) | P2 (AEND) | P3 (CrSNDT) | P4(MAROVISZ) | P5(RELACRE) | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Staff costs | 8640 | 6822 | 8130 | 8040 | 5442 | 7920 | 44994 |
|  | Travel | 2920 |  | 2920 | 2520 | 2520 | 2920 | 13800 |
|  | Subcontracting |  |  |  |  |  |  | 0 |
|  | Equipment | 800 |  |  |  |  |  | 800 |
|  | Others | 1500 |  |  |  |  |  | 1500 |
|  | Indirect costs | 750 | 750 | 750 | 750 | 750 | 750 | 4500 |
|  | Total | 14610 | 7572 | 11800 | 11310 | 8712 | 11590 | 65594 |

WORK PACKAGE 5:		DISSEMINATION AND PUBLICITY

- TRANSFER PROQUALINDT foresees the performance by the members of a continuous dissemination of both the project (objectives, needs, etc.) and intermediate and final results of it.

- Among the objectives of this work package will be to disseminate and transfer the project results to companies, organizations, trainers, etc. (final beneficiaries of the project) and to establish a continuous contact with them and interact with them so as to ensure the proper understanding of the results achieved with the project (guides and manuals for teachers and students).

- Activities descriptions. Tasks.

All partners will participate in dissemination activities of the project, organizing meetings with the parties / agents interested in it. Contacts with these agents (training institutions and companies related to the NDT, unions, employers, public administrations, professional associations, etc.), will continue throughout the development of the project, in which they will be informed of the progress of the project, resolutions adopted, etc.. In this way the interest will be maintained in the project encouraging their future involvement in the results obtained.

In the final steps of the project, there will be a presentation of the products already finished in each and every one of the participating countries, and to which all the agents mentioned above will be invited. To this end, each partner will develop with their own means, at least 200 leaflets that contain an extract of the achievements and results of the project, and they will be used as a cover letter in the dissemination events to be organized.

On the other hand, and taking advantage of the presence of members participating in various events and European organizations, the project will be presented in these events, to give the widest circulation within Europe. In this regard it is noteworthy that all members are full members of the EFNDT. It also coincides with the European NDT Conference (ECNDT) which is held every four years and is the most important event at the European level as regards to NDT is concerned, it will be held in the Czech Republic in 2014 led by CNDT, just after the complexion of the project, so that the dissemination of the project at the highest level within the world of NDT is guaranteed.

In order to give continuity to the project in time, beyond the lifetime of the same, the CNFPO will develop a website with accurate information about the project and the content will be agreed by all partners. In this last phase of the project, and once all the dissemination materials are available (triptychs, website, posters, etc.), a final meeting of all partners in Croatia will be held, coinciding with the dissemination events in that country, and will be used to be able to perform an evaluation of the work done, and plan different strategies for future dissemination and implementation of the products obtained.

| WP5 |  | P0 (CNFPO) | P1(CNDT) | P2 (AEND) | P3 (CrSNDT) | P4(MAROVISZ) | P5(RELACRE) | Total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Staff costs | 5760 | 4548 | 5420 | 5360 | 3628 | 5280 | 29996 |
|  | Travel | 2888 | 2488 | 2888 |  | 2488 | 2888 | 13640 |
|  | Subcontracting | 6000 |  |  |  |  |  | 6000 |
|  | Equipment |  |  |  |  |  |  | 0 |
|  | Others | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 12000 |
|  | Indirect costs | 500 | 500 | 500 | 500 | 500 | 500 | 3000 |
|  | Total | 17148 | 9536 | 10808 | 7860 | 8616 | 10668 | 64636 |