## WP1 MANAGE
WORKING METHODOLOGY (Quality Plan) |  | TOI Project nº: 2011-1-ES1-LEO05-35751 Date:08/03/13 REV 3
W.P. 1: MANAGEMENT, COORDINATION AND EVALUATION
No | Tasks | Responsable | On work |  | Finished/Validated |  |  |  | Evaluation
[5 empty] | Foreseen Date |  | Real Date | Comments | Days | Califfication | Result
1 | To elaborate document Working Methodology | CNFPO |  | x | 2012-02-08 | x | 2012-02-08 |  | 0 | 10 | Optimum
2 | To elaborate document Style Manual | CNFPO |  | x | 2012-02-08 | x | 2012-09-17 |  | 219 | 5 | Acceptable
3 | Six months reports | CNFPO
3.1 | 1st six month report | CNFPO |  |  | 2012-04-30 |  | 2012-09-18 | (1) short time completion | 138 | 0 | Unsatisfactory
3.2 | 2nd six month report | CNFPO |  | x | 2012-10-31 | x | 2012-11-27 | (2) delay in sending reports | 27 | 6.6 | Acceptable
3.3 | 3rd six month report | CNFPO |  |  | 2013-06-30 |  |  |  | 0 | 10 | Optimum
3.4 | 4th six month report | CNFPO |  |  | 2013-12-31 |  |  |  | 0 | 10 | Optimum
4 | Interim report | CNFPO |  | x | 2012-11-30 | x | 2012-11-30 | Not approved (3) | 0 | 10 | Optimum
5 | Final report | CNFPO |  |  | 2014-01-31 |  |  |  | 0 | 10 | Optimum
6 | International meetings | CNFPO
6.1 | 1st Meeting | CNFPO |  | x | 2012-02-08 | x | 2012-02-08 |  | 0 | 10 | Optimum
6.2 | 2nd Meeting | RELACRE |  | x | 2012-09-17 | x | 2012-09-18 |  | 1 | 10 | Optimum
6.3 | 3rd Meeting | CNDT |  | x | 2013-03-06 | x | 2013-03-07 |  | 1 | 10 | Optimum
6.4 | 4th Meeting | CrNDT |  |  | 2013-10-11 |  |  |  | 0 | 10 | Optimum
[9 empty] | TOTAL | 8.4667 | Optimum
Observations:(1) The actual date of beginning of the project was in February, so making a report in April has no sense. (2) Delay in seding reports from partners to promoter. Review in next meeting.(3) Work calendar revision. Request an extension of the end of the project and the 2nd payment again. All new Quality Plan dates are according with the new work calendar which is pending approval by the Spanish Agency.
TRANSFERING EUROPEAN TRAINING PROGRAMME FOR THE QUALIFICATION OF NDT PERSONNEL

## WP2 REVIEW
WORKING METHODOLOGY (Quality Plan) |  | TOI Project nº: 2011-1-ES1-LEO05-35751 Date:08/03/13 REV 3
W.P. 2:REVIEW AND UPDATE
Nº | Tasks | Responsable | On work |  | Finished/Validated |  |  |  | Evaluation
[5 empty] | Foreseen Date |  | Real Date | Comments | Days | Califfication | Result
Sending the Didactic Guidelines to the rest of partners for revision
1 |  | CNFPO |  | x | 2011-12-01 | x | 2011-12-15 |  | 14 | 9.2 | Optimum
2 | Validation of the Didactic Guidelines | AEND |  | x | 2013-09-01 |  |  | ** | 0 | 10 | Optimum
3 | Sending final version of the Didactic Guidelines | CNFPO |  |  | 2013-09-01 |  |  | ** | 0 | 10 | Optimum
4 | Sending the Study Manuals to the rest of partners | CNFPO
4.1 | Sending PT Manuals | AEND |  |  | 2013-09-01 |  |  | ** | 0 | 10 | Optimum
4.2 | Sending MT Manuals | AEND |  |  | 2013-09-01 |  |  | ** | 0 | 10 | Optimum
4.3 | Sending UT Manuals | AEND |  |  | 2013-09-01 |  |  | ** | 0 | 10 | Optimum
4.4 | Sending RT Manuals | AEND |  |  | 2013-09-01 |  |  | ** | 0 | 10 | Optimum
4.5 | Sending ET Manuals | AEND |  |  | 2013-09-01 |  |  | ** | 0 | 10 | Optimum
Validation and sending of final version of the Study Manuals
5 |  | AEND
5.1 | Validation PT Manuals | CNFPO |  |  | 2013-09-30 |  |  | ** | 0 | 10 | Optimum
5.2 | Validation MT Manuals | CNFPO |  |  | 2013-09-30 |  |  | ** | 0 | 10 | Optimum
5.3 | Validation UT Manuals | CNFPO |  |  | 2013-09-30 |  |  | ** | 0 | 10 | Optimum
5.4 | Validation RT Manuals | CNFPO |  |  | 2013-09-30 |  |  | ** | 0 | 10 | Optimum
5.5 | Validation ET Manuals | CNFPO |  |  | 2013-09-30 |  |  | ** | 0 | 10 | Optimum
Validation and sending of final version of the Teacher's guide
6 |  | CNFPO |  | x | 2013-03-30 |  |  | ** | 0 | 10 | Optimum
Observations: New dates for sending and validation of Didactic guides according with the decssion of 2nd meeting and the revised calendar. (**) New dates are introduced according with the decission of the 3rd meeting in Prague
[9 empty] | TOTAL | 9.9429 | Optimum
TRANSFERING EUROPEAN TRAINING PROGRAMME FOR THE QUALIFICATION OF NDT PERSONNEL

## WP3 TRANSFER
WORKING METHODOLOGY (Quality Plan) |  | TOI Project nº: 2011-1-ES1-LEO05-35751 Date:08/03/13 REV 3
W.P. 3: TRANSFER AND TRANSLATION
Nº | Tasks | Responsable | On work | Finished/Validated |  |  | Evaluation
|  |  |  | Foreseen Date | Real Date | Comments | Days | Califfication | Result
1 | To translate Didactic Guidelines at own language
1.1 | Translatoin of all Didactic Guides to Czech | CNDT |  | 2013-11-01 |  |  | 0 | 10 | Optimum
1.2 | Translatoin of all Didactic Guides to Portuguesse | RELACRE |  | 2013-11-01 |  |  | 0 | 10 | Optimum
1.3 | Translatoin of all Didactic Guides to Hungarian | MAROVISZ |  | 2013-11-01 |  |  | 0 | 10 | Optimum
1.4 | Translatoin of all Didactic Guides to Croatian | CrNDT |  | 2013-11-01 |  |  | 0 | 10 | Optimum
2 | To translate PT Manuals to own language
2.1 | To translate PT Manuals to Czech | CNDT |  | 2013-11-01 |  |  | 0 | 10 | Optimum
2.2 | To translate PT Manuals to Portuguesse | RELACRE |  | 2013-11-01 |  |  | 0 | 10 | Optimum
2.3 | To translate PT Manuals to Hungarian | MAROVISZ |  | 2013-11-01 |  |  | 0 | 10 | Optimum
2.4 | To translate PT Manuals to Croatian | CrNDT |  | 2013-11-01 |  |  | 0 | 10 | Optimum
3 | To translate MT Manuals to own language
3.1 | To translate MT Manuals to Czech | CNDT |  | 2013-11-01 |  |  | 0 | 10 | Optimum
3.2 | To translate MT Manuals to Portuguesse | RELACRE |  | 2013-11-01 |  |  | 0 | 10 | Optimum
3.3 | To translate MT Manuals to Hungarian | MAROVISZ |  | 2013-11-01 |  |  | 0 | 10 | Optimum
3.4 | To translate MT Manuals to Croatian | CrNDT |  | 2013-11-01 |  |  | 0 | 10 | Optimum
4 | To translate UT Manuals to own language
4.1 | To translate UT Manuals to Czech | CNDT |  | 2013-11-01 |  |  | 0 | 10 | Optimum
4.2 | To translate UT Manuals to Portuguesse | RELACRE |  | 2013-11-01 |  |  | 0 | 10 | Optimum
4.3 | To translate UT Manuals to Hungarian | MAROVISZ |  | 2013-11-01 |  |  | 0 | 10 | Optimum
4.4 | To translate UT Manuals to Croatian | CrNDT |  | 2013-11-01 |  |  | 0 | 10 | Optimum
5 | To translate RT Manuals to own language
5.1 | To translate RT Manuals to Czech | CNDT |  | 2013-11-01 |  |  | 0 | 10 | Optimum
5.2 | To translate RT Manuals to Portuguesse | RELACRE |  | 2013-11-01 |  |  | 0 | 10 | Optimum
5.3 | To translate RT Manuals to Hungarian | MAROVISZ |  | 2013-11-01 |  |  | 0 | 10 | Optimum
5.4 | To translate RT Manuals to Croatian | CrNDT |  | 2013-11-01 |  |  | 0 | 10 | Optimum
6 | To translate ET Manuals to own language
6.1 | To translate ET Manuals to Czech | CNDT |  | 2013-11-01 |  |  | 0 | 10 | Optimum
6.2 | To translate ET Manuals to Portuguesse | RELACRE |  | 2013-11-01 |  |  | 0 | 10 | Optimum
6.3 | To translate ET Manuals to Hungarian | MAROVISZ |  | 2013-11-01 |  |  | 0 | 10 | Optimum
6.4 | To translate ET Manuals to Croatian | CrNDT |  | 2013-11-01 |  |  | 0 | 10 | Optimum
7 | To translate Teacher's guide to own language
7.1 | To translate Teacher's Guide to Czech | CNDT |  | 2013-05-31 |  |  | 0 | 10 | Optimum
7.2 | To translate Teacher's Guide to Portuguesse | RELACRE |  | 2013-05-31 |  |  | 0 | 10 | Optimum
7.3 | To translate Teacher's Guide to Hungarian | MAROVISZ |  | 2013-05-31 |  |  | 0 | 10 | Optimum
7.4 | To translate Teacher's Guide to Croatian | CrNDT |  | 2013-05-31 |  |  | 0 | 10 | Optimum
Observations: New dates are introduced in the Prague meeting
[7 empty] | TOTAL | 10 | Optimum
TRANSFERING EUROPEAN TRAINING PROGRAMME FOR THE QUALIFICATION OF NDT PERSONNEL

## WP4 EDITION
WORKING METHODOLOGY (Quality Plan) |  | TOI Project nº: 2011-1-ES1-LEO05-35751 Date:08/03/13 REV 3
W.P. 4: EDITION
Nº | Tasks | Responsable | On work | Finished/Validated |  |  | Evaluation
|  |  |  | Foreseen Date | Real Date | Comments | Days | Califfication | Result
1 | To check Didactic Guides are adpted to Style Manual
1.1 | Spanish Didactic Guides | CNFPO |  | 2013-11-30 |  |  | 0 | 10 | Optimum
1.2 | English Didactic Guides | AEND |  | 2013-11-30 |  |  | 0 | 10 | Optimum
1.3 | Czech Didactic Guides | CNDT |  | 2013-11-30 |  |  | 0 | 10 | Optimum
1.4 | Portuguesse Didactic Guides | RELACRE |  | 2013-11-30 |  |  | 0 | 10 | Optimum
1.5 | Hungarian Didactic Guides | MAROVISZ |  | 2013-11-30 |  |  | 0 | 10 | Optimum
1.6 | Croatian Didactic Guides | CrNDT |  | 2013-11-30 |  |  | 0 | 10 | Optimum
2 | To check Study Manuals are adapted to Style Manual
2.1 | Spanish Study Manuals | CNFPO |  | 2013-11-30 |  |  | 0 | 10 | Optimum
2.2 | English Study Manuals | AEND |  | 2013-11-30 |  |  | 0 | 10 | Optimum
2.3 | Czech Study Manuals | CNDT |  | 2013-11-30 |  |  | 0 | 10 | Optimum
2.4 | Portuguesse Study Manuals | RELACRE |  | 2013-11-30 |  |  | 0 | 10 | Optimum
2.5 | Hungarian Study Manuals | MAROVISZ |  | 2013-11-30 |  |  | 0 | 10 | Optimum
2.6 | Croatian Study Manuals | CrNDT |  | 2013-11-30 |  |  | 0 | 10 | Optimum
3 | To print triptychs | ALL |  | 2013-08-31 |  |  | 0 | 10 | Optimum
4 | To edit a CD with all materials | CNFPO |  | 2013-11-30 |  |  | 0 | 10 | Optimum
Observations: New dates are introduced in the Prague meeting
[7 empty] | TOTAL | 10 | Optimum
TRANSFERING EUROPEAN TRAINING PROGRAMME FOR THE QUALIFICATION OF NDT PERSONNEL

## WP5 DISSEMIN
WORKING METHODOLOGY (Quality Plan) |  | TOI Project nº: 2011-1-ES1-LEO05-35751 Date:08/03/13 REV 3
W.P. 5: DISSEMINATION AND PUBLICITY
Nº | Tasks | Responsable | On work |  | Finished/Validated |  |  |  | Evaluation
[5 empty] | Foreseen Date |  | Real Date | Comments | Days | Califfication | Result
1 | Project Results presentation
| Spain | CNFPO* |  |  | 2013-12-15 |  |  | (*) AEND | 0 | 10 | Optimum
| Czech Republic | CNDT |  |  | 2013-12-15 |  |  |  | 0 | 10 | Optimum
| Crotaia | CrNDT |  |  | 2013-12-15 |  |  |  | 0 | 10 | Optimum
| Hungary | MAROVISZ |  |  | 2013-12-15 |  |  |  | 0 | 10 | Optimum
| Portugal | RELACRE |  |  | 2013-12-15 |  |  |  | 0 | 10 | Optimum
2 | Web page of project | CNFPO |  | x | 2013-08-31 | x | 2012-09-25 |  | 0 | 10 | Optimum
Observations:
[9 empty] | TOTAL | 10 | Optimum
TRANSFERING EUROPEAN TRAINING PROGRAMME FOR THE QUALIFICATION OF NDT PERSONNEL