Leonardo da Vinci Programme

WORKING METHODOLOGY

INDEX

1	aim	3

2	COMMUNICATIONS AMONG PARTNERS  	3

3	INTERNATIONAL MEETINGS	3

4	RESULTS OF THE PROJECT. FINAL PRODUCTS	4

5	QUALITY PLAN. EVALUATION AND MONITORING	4

6	DEVELOPMENT OF THE PROJECT. INCIDENCES	5

ANNEX 1. quality plan	7

# Aim

The aim of this document is setting the basis for the procedures and actions to be developed during the project, in order to assure a smooth development and the fulfilment of the foreseen aims within some minimum quality.

- Once revised and accepted by all the partners participating, the content of this document should be a reference of obliged use compulsory fulfilment for all the partners.

# COMMUNICATIONS AMONG PARTNERS

The natural mean of communication is e-mail. Conversely, fax could be an alternative mean.

To that end a contact person will be appointed, and a second person in case of absence of the first one.

In case of any change in the appointed person, the promoter should be informed immediately, who in turn shall inform all the partners.

The receiver of any communication by other partner shall be obliged to confirm the proper reception of the message.

Mail will only be used to send original documents (original certificates, minutes or contracts duly signed and stamped), using the most reliable and fastest mean (urgent and certified mail).

Working documents enclosed to the messages will be written necessarily in Word, Excell or Access (Microsoft Office 2003 or previous versions). Those documents written only for reading purposes could be in pdf (Adobe Acrobat Reader).

Working language is English and in this language all communications will be transmitted.

# INTERNATIONAL MEETINGS

Once agreed the number of meetings and dates, all members are obliged to attend the aforementioned meetings.

Meetings will be summoned by the host country in cooperation with the promoter and must be done 40 days minimum before the event. Furthermore the host country is in charge of defining the agenda of the meeting together the promoter and prepares everything accordingly, including the logistic support which could be required by the rest of partners.

At the end of each meeting the host partner will write the minutes including all the agreements, and also possible amendments regarding activities and budgets. The minutes of the meetings will be sent by the promoter for approval to the rest of the members within ten days. The minutes were signed at the next meeting.

Minutes signed by all the partners will be considered as annexes to the original signed contracts among promoter and partners.

# RESULTS OF THE PROJECT. FINAL PRODUCTS

All the products considered as a result of the project (didactic guides, study manuals, ...) are the property of the partners.

Before publishing any product, it must be approved by the Promoter-Contractor of the project, since it must include information related to the co-funding of the European Commission.

It is not allowed any commercialization of the products deriving from the project along its life, except for agreement of all the members, who will determine the foreseen exploitation of these when the project is finished and once concluded the contractual period.

# QUALITY PLAN. EVALUATION AND MONITORING

A quality plan will be established in which the observed deviations can be identified, correcting measures could be proposed and a monitoring process could be applied. For that the above mentioned plan must include control activities, evaluation and monitoring which should be fixed in the following aspects:

- Verify the fulfilment of the foreseen aims and results. Quality Plan must to include items easily identifiable (tasks) which let evaluate them in order to we can to obtain the degree of advance of the project on every phase or work package.

- Check that the contents are not opposed to the provisions of the standards (EN473, ISO9712, UNE-CEN-ISO/TR 25107).

Once we have specified the rules to be considered as reference in each document, an interim control must be done to watch the partners´ compliance with the meted assigned, in the work packages 2 and 3 referring to didactic guides and study manuals, and must be validated by all members.

- Check that rules included in the style manual are fulfilled.

All final products must submit to this control before definitive printing. This revision must be accomplished by the partners during the process of products elaboration.

In order to do a monitoring and evaluation of the project during execution period, the following controls will be established:

- Elaboration of a report each six months. This must be done by the promoter and it should be included the degree of advance of the project, managed aims, foreseen activities and state of the budget. To that end all the partners must remit the promoter in a 15 days period from promoter's request, all available information, using the boxes included in the form within Intermediate Report. Four points of control will be done in the months 6th, 12th, 18th and 24th of the project. The reports of the months 12th and 24th will be used respectively for the writing of the Intermediate and Final Reports, which must be remitted by the promoter to the National Agency for its approval.

- International Meetings. All the meetings celebrated during the project (excepting the first one) must include within the topics of the agenda, an evaluation which allow us to determine the degree of advance of the project.

# DEVELOPMENT OF THE PROJECT. INCIDENCES

All partners must know and correctly apply the Administrative and Financial Manual currently ruling this project. Should you have any doubts, address it to the promoter who must answer in the shortest period on the basis of attending the different questioned raised by Leonardo Spanish Agency, responsible of this project.

Except for exceptions, any alteration affecting the activities and the foreseen contract obligations, require the approval and in some cases an addenda to the main contract subscribed between the contractor and the National Agency. Bearing this in mind any alteration must have the support of all the members and the acceptance of the National Agency.

Any activity accomplished by any member affecting the budget without being backed by all members, and contravenes the Administrative and Financial Manual, it will be under its entire responsibility.

# ANNEX 1

QUALITY PLAN

EVALUATION AND MONITORING

- AIM OF THE QUALITY PLAN

To get a tool which will be used to watch and verify the fulfilment of all foreseen tasks and results of the project on every one of the phases or work packages.

- PROCEDURE FOR THE ELABORATION OF THE QUALITY PLAN

  - To identify items  which to be easy to check them:

Tasks and results

  - To find some aspect or characteristic belonged to every item which to be able to measure:

Foreseen date and real date of realisation

  - To evaluate the finished items

Attending to the difference of days between the foreseen date and the real date of realisation.

  - To observe the evaluation results and to propose correct means if they were necessaries.

If the result of any item is 5 or minor

- EVALUATION

Attending to difference of days between the foreseen date and the real date of realisation

<= 10 days = 10 points

> 10 days = 10 - [0,2 x (difference of days -10)] points

If the task is finished the minimum score for that item will be 5 points

- EVALUATION RESULT

Global* score between 10 & 7, will be qualified as "optimum"

Global score between 7 & 5, will be qualified as "acceptable"

Global score between 5 & 0, will be qualified as “unsatisfactory"

*Global term do reference at total score in any work package.

In any case, global qualification "acceptable" or “unsatisfactory" (at the total of a work package), or a particular qualification “unsatisfactory" in any item, will be subject to discuss in order to detect the cause of that deviation.